LUCKNOW CITY RUN

DAY 0 CHECKLIST
Submitted by: Shivam Pathak

| Line Item | Number | Positioning | POC Name & Number |
| --- | --- | --- | --- |
| Security |  |  |  |
| Barricades |  |  |  |
| PCR Vans |  |  |  |
| Police men |  |  |  |
| Security Volunteers |  |  |  |
| Infrastructure |  |  |  |
| Chairs |  |  |  |
| Tables |  |  |  |
| Tents |  |  |  |
| Stalls |  |  |  |
| Portable Washrooms |  |  |  |
| Sound System – Speakers, Mics |  |  |  |
| Promotional |  |  |  |
| Banners - Overhead |  |  |  |
| Banners - Poles |  |  |  |
| Banners - Stalls |  |  |  |
| Banners - Barricades |  |  |  |
| Photo Booth |  |  |  |
| F&B |  |  |  |
| Water Bottles |  |  |  |
| Sports Drinks/Juices |  |  |  |
| Packed Food Boxes |  |  |  |
| Food vendors |  |  |  |
| Administrative Documents |  |  |  |
| Venue Permissions |  |  |  |
| Food & Stall Permissions |  |  |  |
| MoU/MoA prints |  |  |  |
| Declarations |  |  |  |
| Event Documents |  |  |  |
| Registration Sheet |  |  |  |
| Participant Details |  |  |  |
| Number Tag Prints |  |  |  |
| Certificates |  |  |  |
| Medical Emergency |  |  |  |
| First-Aid Kits |  |  |  |
| Ambulance Stand-by |  |  |  |
| Miscellaneous |  |  |  |
| Start Line Flags |  |  |  |
| Finish Line Ribbon |  |  |  |
| Watch |  |  |  |

ENVIRONMENTAL CHECKLIST

| LINE ITEM | STATUS | POC |
| --- | --- | --- |
| Road Cleanliness |  |  |
| Gomti River Water Level |  |  |

Banners

Timelines:

[T-30] 		Locating vendors & negotiating quotes

[by T-25] 	Vendor confirmation

[by T-15] 	Sending Designs to Vendors

[by T-10]	Locate installation staff helpers, if not available through printer

[by T-10] 	Sample print check

[by T-5] 	Banner Delivery to IIM Lucknow

[by T-4]	Quality Check

[by T-2]	Reprints, if any required

[T-1 & T-0]	Banner Transportation to Event Locations

[T-1 & T-0]	Installation with Helper Staff

[T-0]		Banner removal & salvage

# of banners required:

| Type | Number | Specifics |
| --- | --- | --- |
| Cross-Road Banners – 3x1m length | 15 | - Welcome Banner – 1 - “xx kms left” – 10 - Finish line – 1 - Stalls - 3 |
| A4 size pole posters | 160 | - Streetlights, barricades, stalls – 150 - In Campus – 10 |
| Large-Scale Banners – 3x5m | 3 | - In campus promotion - City Run Entry Area - City Run Exit Area |
| Side Banners – 1.5x0.5m length | 110 | - Barricades – 100 (includes sponsor brands banners) - Water/Sports Drink Stands – 10 |
| Total | ~300 |  |

Negotiation:

- Basis quantity of banner

- Basis quality of banner

- Basis past/future customer value