ROUND 3 – PLANNING OF PRO SHOW AT UMANG-UTSAV GROUNDS

General Idea

As discussed, the reason for choosing Umang-Utsav ground is because we have both external and internal participants.

Inside the campus, it would get difficult to manage the external crowd, and it would also become difficult to keep track of them. Thus, Umang-Utsav gives is the most feasible solution for us.

Legends used

Yellow Line – Barricading

Red Line – Flow of crowd

General Stage

Infront of the stage, the organisation would be in the following order:

- Faculty Box – Chairs would be provided for the faculties

- VIP Box – No chairs. but would get closer space to the stage. Both students and external crowd can buy tickets for VIP Box.

Note : For external crowd, ticket would be priced atleast 1.5 times the price of the IIM L students.

- General crowd – Crowd consisting of both IIM L students as well as  external crowd.

Note : For external crowd, ticket would be priced atleast 1.5 times the price of the IIM L students.

Checkpoints and Bouncers:

We have a total of 3 checkpoints built for our Pro-Show. At each checkpoint, bouncers and volunteers would be present to check the bands/passes of the visitors.

3 checkpoints would also ensure that there is no overcrowding at one, and the crowd is better managed.

All the bouncers would have a Walkie talkie for ease of communication.

- Checkpoint 1 – The main Umang gate. At this checkpoint, bands of everybody would be checked. Since we have 2 gates for entry, we would use the 2 gates for the following reason:

- Gate 1 –  Paid Parking Area. For external crowd, some might have personal vehicles, and to facilitate parking, we would need to have Parking for them. This gate would act as a ticket counter where vehicles would purchase ticket for parking the vehicles. Cost of ticket:

    - 4 wheelers – Rs 250/hr

    - 2 wheelers – Rs 100/hr

The prices are kept higher so as to discourage external crowd to bring personal vehicles (This would lead to better crowd management)

The external crowd would be able to enter the Parking once all the passes/bands have already been verified by the bouncers at Checkpoint 1.

Total bouncer required: 2 (Both Male)

- Gate 2 – Gate 2 would have 2 different kinds of entry.

    - Special entry – For faculties, performing artists, and the MV Core Members.

    - General entry – For college students and external crowd.

Bouncers required –

- Special entry – 1 (Male)

- General entry – 2 (Male)

After entering checkpoint 1, the visitors are free to explore the food stalls. They would travel towards Umang (where the food stalls have been kept) or they could directly go to checking 2.

- Checkpoint 2 – At checkpoint 2, there is a separation.

- Faculties, Artists, Core members – Band check.

Bouncers Required – 2 (1 Male, 1 female)

- General Entry (Students and external crowd) – Band check

Bouncers Required – 2 (1 Male, 1 female)

Volunteers required – 4 (To assist the bouncers)

At checkpoint 2, we have 2 different bifurcation leading to faculty and general area.

- Checkpoint 3 – Final Checkpoint. This would lead to the assembly area for the crowd.

Faculty area/ VIP Area – Designated right in front of the stage.

Bouncers Required - 1

General Area – Right behind the VIP area, for students and general crowd.

Bouncers Required – 1

Total Number of Bouncers Required

Up until now, for checkpoints we would require:

2+3+2+2+1+1 = 11

Number of bouncers in front of stage – 2

Number of bouncers at Green Room – 1

Number of bouncers at general equipment – 1

Number of bouncers doing rounds, and for buffer activities – 3

Total bouncers required = 18

Total cost of bouncers @ 1200 per bouncer = 18*1200

= Rs 21600

So approx. 20,000 to 22,000 would be required for hiring of bouncers.

Parking

As Parking is for external crowd, where fees is being charged as already discussed. The external crowd would be able to enter the Parking once all the passes/bands have already been verified by the bouncers at Checkpoint 1.

Additionally, A PCR Van would be parked at the closed area to the gate in case of an emergency. The additional 3 bouncers should be able to assist the PCR Van out of the compound in case of an emergency.

Food Stalls

We have to set up food stalls, as shown in the diagram. The area would be completely barricaded and 3 bouncers would be on round so as to avoid any nuisance.

General Equipment Area

General equipment would include – Generators, Additional equipment for the artists, escort vehicles, and police vehicles (in case we have the police)

Green Room

Right beside our Stage, to the right of it would be the green room for the Artists. 1 bouncer would be present here for artists safety.

Washroom

Utsav’s washroom could be used for the crowd. There would be separate entry-exit points for different crowds.